# Software Project Management Plan

# AssetAtlas Web Application

# May 1, 2021

# Team Members

# Fardowsa Muhumed

# Imanol Ramirez

# Ashli Johnson

# Travon Cross

## Document Control

### Change History

| Revision | Change Date | Description of changes |
| --- | --- | --- |
| V1.0 | 05/01/2026 | Initial release |

### Document Storage

This document is stored in the project's Git repository at:
https://github.com/ashlinjohnson/Capstone_Project

Additional project documents and assets are stored in the team's Google Drive folder at:
https://drive.google.com/drive/folders/13nkU5rMXic4u0EmYyCLt71OMjird5Dcf?usp=sharing

### Document Owner

Fardowsa Muhumed is responsible for developing and maintaining this document.

## Table of Contents

1 Overview…………………………………………………………………………4
1.1 Purpose and Scope…………………………………………………………………………….4
1.2 Goals and Objectives………………………………………………………………………….4
1.3 Project Deliverables…………………………………………………………………………...5
1.4 Assumptions and Constraints…………………………………………………………………5 
1.5 Schedule and Budget Summary………………………………………………………………6 
1.6 Success Criteria……………………………………………………………………………….8 
1.7 Definitions…………………………………………………………………………………….8 
1.8 Evolution of the Project Plan…………………………………………………………………9

2 Startup Plan……………………………………………………………………..9 
2.1 Team Organization……………………………………………………………………………9 
2.2 Project Communications……………………………………………………………………..10 
2.3 Technical Process…………………………………………………………………………….11
2.4 Tools………………………………………………………………………………………….11

3 Work Plan………………………………………………………………………13 
3.1 Activities and Tasks………………………………………………………………………….13
3.2 Release Plan………………………………………………………………………………….14 
3.3 Iteration Plans………………………………………………………………………………..15 
3.4 Budget………………………………………………………………………………………..16

4 Control Plan……………………………………………………………………17 
4.1 Monitoring and Control……………………………………………………………………..17 
4.2 Metrics Collection…………………………………………………………………………..18

5 Supporting Process Plans……………………………………………………..18 
5.1 Risk Management Plan……………………………………………………………………...18
5.2 Configuration Management Plan……………………………………………………………19 
5.3 Verification and Validation Plan…………………………………………………………….19 
5.4 Product Acceptance Plan……………………………………………………………………20

## 1 Overview

### 1.1 Purpose and Scope

The purpose of AssetAtlas is to provide users with a secure, cloud-deployed financial asset tracking and management platform that enables individuals to monitor personal finances across multiple accounts, track expenses, perform transfers, manage debt payoff, and visualize spending patterns through interactive charts. The application addresses the growing need for accessible, user-friendly financial tools.

Project scope defines the boundaries of the project. AssetAtlas will be a full-stack web application that includes:

- User registration and authentication with hashed passwords (bcrypt)

- Dashboard with pie chart of categorized expenses

- Budget tracking and expense categorization

- User profile management with settings and password reset

- Transaction categorization from uploaded bank statements/receipts

- Deploy to cloud/Windows server (stretch goal)

- Savings progress page with visual tracking

- Debt payoff page with timeline projections

- Itemized expenditures page (color-coded, recurring subscriptions section)

- Responsive front-end using Tailwind CSS

- React frontend framework

- Flask REST API layer

- PostgreSQL database

- File logging for errors

- Security scanning via OWASP ZAP (zero Critical issues)

- Accessibility audit compliance

Out of scope includes:

- Actual payment processing or real credit card transactions

- Mobile native applications

- Third-party bank API integrations (e.g., Plaid)

- Multi-currency support

- Bill payment functionality

### 1.2 Goals and Objectives

Project goals:

- Deliver a functional full-stack web application that meets all Commerce Bank Capstone requirements.

- Create an intuitive financial tracking tool accessible to users regardless of technical knowledge.

- Demonstrate professional software development practices including testing, security, and documentation.

- Successfully deploy the full-stack application (React + Flask + PostgreSQL) to a cloud or Windows server environment with environment-specific configurations for development, staging, and production.

Project objectives (SMART):

- Complete user authentication with password hashing by March 15, 2026.

- Implement database schema and API endpoints by March 29, 2026.

- Deploy to cloud/Windows server integration by April 12, 2026.

- Complete all pages and OWASP ZAP security scan (zero Critical issues) by April 26, 2026.

- Complete final testing, accessibility audit (zero errors), and bug fixes by May 3, 2026.

- Deliver final presentation with working application walkthrough by May 8, 2026.

### 1.3 Project Deliverables

The following items will be delivered to Commerce Bank on or before May 8, 2026:

- Source code for both backend (Flask) and frontend (React)

- Deployed application accessible via cloud instance URL

- Database schema and Alembic migration scripts

- OWASP ZAP security scan report with documented fixes for all Critical issues

- Accessibility audit report (axe/WAVE) showing zero errors

- Backend unit test suite (pytest, minimum 70% coverage)

- Frontend component tests (Jest)

- API documentation

- User guide

- Final presentation slides

### 1.4 Assumptions and Constraints

Assumptions:

- The development environment will remain accessible throughout the project.

- Docker and containerization tools will function properly for deployment.

- The PostgreSQL database service will be available for deployment.

- Team members have access to necessary development tools and internet connectivity.

- The Commerce Bank tech mentor team will respond to questions within reasonable timeframes (Zoom calls Tue/Thu after 7 PM).

- Users can upload PDF/image/CSV files for transaction extraction.

Constraints:

- The software must be a web application (no CMS like WordPress).

- Must use a CSS framework (Tailwind CSS).

- Must use a JavaScript framework/library (React).

- The database must be PostgreSQL with hashed passwords (bcrypt).

- Must be deployed to a cloud instance (AWS Free Tier, GCP Free Tier, or Azure for Students).

- Must be security scanned using OWASP ZAP with zero Critical issues.

- Must pass an accessibility audit with zero errors.

- Session persistence must remember users across browser restarts.

- Self-hosted authentication with password reset capability is required.

- Must include one stretch goal: Deploy to cloud/Windows server.

- The software must be ready by May 8, 2026.

### 1.5 Schedule and Budget Summary

Schedule Summary:

| Date | Milestone |
| --- | --- |
| February 4, 2026 | Project start. Team formed, roles assigned. |
| February 19, 2026 | Requirements finalized (SRS complete) + architecture laid out. |
| February 26, 2026 | Frontend, backend, and database communication working. |
| March 15, 2026 | Iteration 1 complete. Login/register and basic dashboard functional. |
| March 29, 2026 | Iteration 2 complete. Database schema complete and all API endpoints functional. |
| April 12, 2026 | Iteration 3 complete. Deploy to cloud/Windows server |
| April 26, 2026 | Iteration 4 complete. All pages complete, OWASP ZAP scan done (zero Critical issues). |
| May 3, 2026 | Final testing, accessibility audit (zero errors), bug fixes complete. |
| May 8, 2026 | Final presentation and working application walkthrough. |

Budget Summary:
Total Project Cost: $0. This is an academic capstone project with no monetary budget.

| Resource | Cost |
| --- | --- |
| GitHub | Free |
| Docker | Free (Community Edition) |
| PostgreSQL | Free (open source) |
| Python/Flask | Free (open source) |
| React | Free (open source) |
| Tailwind CSS | Free (open source) |
| OWASP ZAP | Free (open source) |
| Cloud Hosting | Free tier (AWS/GCP/Azure for Students) |

### 1.6 Success Criteria

The project will be considered a success if:

- All application requirements from the project walkthrough and SRS are implemented.

- Application deploys successfully and is accessible online via cloud URL.

- OWASP ZAP scan shows zero Critical security issues.

- Accessibility audit shows zero errors.

- Backend unit tests pass with minimum 70% coverage.

- Users can register, login, and have persistent sessions.

- Budget tracking, expense logging, savings, and debt payoff features work as demonstrated.

- Stretch goal is delivered: Deploy to cloud/Windows server

- All documentation is complete and up to date.

- Final presentation meets all stakeholder (Commerce Bank) expectations.

### 1.7 Definitions

| Term | Definition |
| --- | --- |
| API | Application Programming Interface - REST endpoints for backend communication |
| Alembic | Database migration tool for SQLAlchemy |
| CMS | Content Management System (e.g., WordPress) |
| CSS Framework | Pre-built styling library (Tailwind CSS) |
| DAP | Developer Acceleration Program at Commerce Bank |
| Flask | Python web framework used for backend |
| OWASP ZAP | Open Web Application Security Project Zed Attack Proxy |
| PostgreSQL | Open source relational database |
| React | JavaScript library for building user interfaces |
| SMART | Specific, Measurable, Attainable, Realistic, Time-bound |

### 1.8 Evolution of the Project Plan

Before the start of an iteration, the project plan will be updated to include a schedule of detailed tasks for the upcoming iteration. At the conclusion of an iteration, the project plan will be updated to include the actual effort for each completed task.

Risk mitigation efforts will be evaluated at the start of each iteration. Severe risks will be analyzed and added to the project plan as soon as they materialize.

## 2 Startup Plan

### 2.1 Team Organization

| Role | Name | Responsibilities |
| --- | --- | --- |
| Project Manager / Documentation Lead | Fardowsa Muhumed | Creating project plan, managing risks, running weekly team meetings, providing status reports to mentors, tracking requirements documentation, user stories, testing documentation, overall project tracking |
| Backend Developer | Ashli Johnson | API development (Flask), business logic, authentication implementation, server-side functionality, API documentation, OWASP ZAP scanning |
| Frontend Developer | Imanol Ramirez | UI implementation (React), Tailwind CSS integration, React component development, frontend testing, accessibility audit (axe/WAVE) |
| Database Administrator | Travon Cross | Database design (PostgreSQL), user password hashing (bcrypt), data integrity, query optimization, Alembic migrations |

Reporting Structure:
All team members report to the Project Manager for project management purposes. The Project Manager reports to Commerce Bank Tech Mentors. All members collaborate directly for technical decisions.

### 2.2 Project Communications

Meeting Schedule:

| Meeting | Frequency | Duration | Participants | Purpose |
| --- | --- | --- | --- | --- |
| Daily Standup | Daily | 15 min | All members | Progress, blockers, daily plan |
| Mentor Check-in | Weekly (Tue/Thu after 7 PM) | 30 min | All members + mentor | Progress review, Q&A, feedback |
| Iteration Planning | Bi-weekly | 60 min | All members | Plan tasks for next iteration |
| Retrospective | End of each iteration | 30 min | All members | Review what went well and what to improve |

Communication Tools:

- Discord – Daily standups and real-time chat

- Zoom – Mentor check-ins and iteration planning

- Email – DLCcommercebankUMKCCapstoneTeam@commercebank.com for mentor questions

- GitHub Issues – Defect tracking and task assignment

Status Reports:
Weekly status report compiled by Project Manager (Fardowsa) every Friday, sent to Commerce Bank mentors.

### 2.3 Technical Process

The team will follow an Agile methodology with 2-week iterations.

Phases:

- Setup and Planning – Week 1

- Core Features (Authentication + Database) – Weeks 2-3

- Financial Features – Weeks 4-5

- Deploy to cloud/Windows server – Week 6

- Testing and Security – Week 7

- Deployment and Polish – Week 8

Workflow:

- Backlog Grooming – Project Manager maintains prioritized feature list (GitHub Issues)

- Iteration Planning – Team selects tasks for upcoming sprint

- Development – Feature branches from main

- Code Review – Pull request requires 2 approvals before merge

- Testing – Unit tests must pass before merge (GitHub Actions CI)

- Review – Working features demonstrated at iteration end

### 2.4 Tools

| Category | Tool |
| --- | --- |
| Programming Languages | Python, JavaScript, HTML, CSS, SQL |
| Version Control | GitHub (repository) |
| Defect Tracking | GitHub Issues |
| Backend Framework | Flask |
| Frontend Framework | React |
| CSS Framework | Tailwind CSS |
| Database | PostgreSQL |
| ORM & Migrations | SQLAlchemy, Alembic |
| Environment | Docker, Docker Compose |
| Build Tools | npm, Docker Compose |
| Backend Testing | pytest (minimum 70% coverage) |
| Frontend Testing | Jest |
| Security Scanning | OWASP ZAP |
| Accessibility Testing | WAVE, axe |
| Communication | Discord, Zoom, Email |
| Documentation | GitHub Wiki, Markdown, Google Docs |

## 3 Work Plan

### 3.1 Activities and Tasks

Phase 1: Project Setup (Completed by February 19, 2026)

- Initialize GitHub repository – Johnson

- Setup Flask backend structure – Johnson

- Configure PostgreSQL with Alembic – Cross

- Initialize React frontend – Ramirez

- Create docker-compose configuration – Johnson

- Create project documentation template – Muhumed

- Finalize requirements and architecture – All

Phase 2: Communication Setup (Completed by February 26, 2026)

- Establish frontend, backend, and database communication – Johnson, Ramirez, Cross

Phase 3: Iteration 1 – Authentication (Completed by March 15, 2026)

- Create User database model – Cross

- Implement password hashing (bcrypt) – Cross

- Build Register API endpoint – Johnson

- Build Login API endpoint – Johnson

- Create Login and Register React pages – Ramirez

- Implement session persistence (remember me) – Johnson

- Create basic dashboard – Ramirez

Phase 4: Iteration 2 – API & Database (Completed by March 29, 2026)

- Complete database schema (expenses, savings goals, debts) – Cross

- Build Expense and Budget API endpoints – Johnson

- Build Savings and Debt API endpoints – Johnson

- Complete all CRUD operations – Johnson

Phase 5: Iteration 3 – Deployment & Production Readiness (Completed by April 12, 2026)

- Deploy full-stack application to cloud/Windows server – Ramirez

- Configure environment properties for dev/staging/prod – Johnson

- Run OWASP ZAP security scan & fix critical issues –  Ramirez

- Run accessibility audit & fix errors – Imanol Ramirez

- Implement session persistence ("Remember Me") – Johnson

- Configure file logging for API errors and authentication – Ramirez

Phase 6: Iteration 4 – Pages & Security (Completed by April 26, 2026)

- Complete Savings Progress page – Ramirez

- Complete Debt Payoff page – Ramirez

- Complete Itemized Expenditures page (color-coded, subscriptions) – Ramirez

- Complete User Profile and Settings page (password reset) – Ramirez

- Run OWASP ZAP security scan – Johnson

- Fix all Critical security issues – Johnson & Cross

- Complete data visualization (pie chart, progress bars) – Ramirez

Phase 7: Final Testing & Audit (Completed by May 3, 2026)

- Write backend unit tests (pytest, 70% coverage) – Johnson

- Write frontend component tests (Jest) – Ramirez

- Run accessibility audit (axe/WAVE) – Ramirez

- Fix all accessibility errors – Ramirez

- Deploy to cloud/Windows server (stretch goal) – Ramirez

- Perform end-to-end testing – All

- Fix any remaining bugs – All

Phase 8: Final Presentation (Completed by May 8, 2026)

- Prepare final presentation slides – Muhumed

- Practice presentation – All

- Deliver final presentation with working application walkthrough – All

- Compile final documentation – Muhumed

### 3.2 Release Plan

| Version | Date | Description |
| --- | --- | --- |
| v0.1 (Internal Alpha) | February 26, 2026 | Frontend, backend, and database communication working |
| v0.2 | March 15, 2026 | Login/register and basic dashboard functional |
| v0.3 | March 29, 2026 | Database schema complete + all API endpoints functional |
| v0.4 | April 12, 2026 | Deploy to cloud/Windows server + file uploads functional |
| v0.5 | April 26, 2026 | All pages complete + OWASP ZAP scan done (zero Critical issues) |
| v1.0 RC | May 3, 2026 | Final testing, accessibility audit (zero errors), bug fixes complete |
| v1.0 (Production) | May 8, 2026 | Final presentation version |

### 3.3 Iteration Plans

| Iteration | Dates | Focus | Deliverables |
| --- | --- | --- | --- |
| Iteration 1 | Feb 19 – Mar 15 | Authentication + Dashboard | User registration, login, session persistence, basic dashboard |
| Iteration 2 | Mar 15 – Mar 29 | Database + API | Complete database schema, all CRUD API endpoints |
| Iteration 3 | Mar 29 – Apr 12 | File Uploads | File upload |
| Iteration 4 | Apr 12 – Apr 26 | Pages + Security | Savings, debt, expenditures pages; OWASP ZAP scan (zero Critical issues) |
| Final Testing | Apr 26 – May 3 | Testing + Audit | Unit tests (70% coverage), accessibility audit (zero errors), error logging |
| Final Presentation | May 8 | Stakeholder presentation | Working app walkthrough, security report, professional presentation |

### 3.4 Budget

Total Project Budget: $0

| Resource | Cost |
| --- | --- |
| GitHub | Free |
| Docker | Free |
| PostgreSQL | Free |
| Python/Flask | Free |
| React | Free |
| Tailwind CSS | Free |
| OWASP ZAP | Free |
| Cloud Hosting | Free tier (AWS/GCP/Azure for Students) |

## 4 Control Plan

### 4.1 Monitoring and Control

| Activity | Frequency | Facilitator | Purpose |
| --- | --- | --- | --- |
| Daily Standup | Daily (15 min) | Muhumed | Status, progress, blockers |
| Iteration Review | End of each 2-week iteration | Muhumed | What was accomplished, what went right/wrong, suggestions |
| Mid-Project Review | March 29, 2026 | Muhumed | Present status to sponsor |
| Final Review | May 8, 2026 | Muhumed | Present final product to sponsors |
| Weekly Mentor Report | Every Friday | Muhumed | Status report to Commerce Bank |
| Code Review | Per pull request | Two approvers | Quality assurance |

### 4.2 Metrics Collection

| Phase | Measurement | Source |
| --- | --- | --- |
| Release Planning | Effort estimates for product features | Project Manager |
| Iteration Planning | Effort estimates for scheduled tasks; updated estimates for features/dates | Project Manager |
| Iteration Closeout | Actual effort for tasks/features; LOC count | Project Manager, Programmers |
| System Test | Rate of errors found | QA (team) |
| Ongoing | Defect categories (blocker, critical, major, minor, trivial); defect states (open, assigned, fixed, closed) | All team members |

## 5 Supporting Process Plans

### 5.1 Risk Management Plan

| # | Risk | Probability | Impact | Mitigation | Contingency |
| --- | --- | --- | --- | --- | --- |
| 1 | Cloud deployment platform limitations/costs | Medium | High | Research free tiers early; test locally first | Use alternative free platform |
| 2 | Security scan reveals Critical vulnerabilities | Medium | High | Run OWASP ZAP early and iteratively; follow secure coding practices | Allocate extra time for fixes; consult mentor |
| 3 | Team member availability conflicts | Low | Medium | Maintain clear documentation; daily check-ins | Reallocate tasks temporarily; use async communication |
| 4 | Cloud deployment environment configuration issues | Medium | Medium | Test deployment early using free tier; use environment variables for all configurations; validate database migrations in staging | Roll back to last known working deployment; allocate extra time for debugging; consult mentor |
| 5 | Accessibility audit failures | Medium | Low | Use semantic HTML; test with screen readers early | Apply suggested fixes; re-audit |
| 6 | Timeline slippage | Medium | High | Track progress weekly; prioritize must-have features | Cut nice-to-have features; focus on requirements |

### 5.2 Configuration Management Plan

- All work products stored in GitHub repository

- Naming convention: NNN-VVV.suffix (e.g., REQ-002.doc)

- Baselined items: System requirements (SRS), project plan (SPMP), source code

- Change control: After baseline, changes require group discussion and vote (2-day response window)

- Change history required for baselined documents (author, description, reason, date)

### 5.3 Verification and Validation Plan

- Code Review: Pull request requires 2 approvals before merging to main

- Unit Tests: pytest for backend (minimum 70% coverage); Jest for frontend

- Integration Tests: pytest for API endpoints and database

- Security Scan: OWASP ZAP – must show zero Critical issues

- Accessibility Audit: axe + WAVE – must show zero errors

- End-to-End Testing: Manual or Playwright for critical user journeys

Validation Checkpoints:

| Date | Validation |
| --- | --- |
| February 26, 2026 | Frontend, backend, DB communication |
| March 15, 2026 | Iteration 1 (authentication + dashboard) |
| March 29, 2026 | Iteration 2 (database + API) |
| April 12, 2026 | Iteration 3 (Deploy to cloud/Windows server) |
| April 26, 2026 | Iteration 4 (all pages + security scan) |
| May 3, 2026 | Security + accessibility validation |
| May 8, 2026 | Final validation (presentation) |

### 5.4 Product Acceptance Plan

Acceptance Criteria (from Commerce Bank DAP requirements):

| Requirement | Status Required |
| --- | --- |
| Full-stack web application (no CMS) | Required |
| PostgreSQL database | Required |
| Hashed user passwords (bcrypt) | Required |
| Login and Register page | Required |
| Home/Dashboard page | Required |
| User Profile and Settings | Required |
| At least 2 additional pages (Savings + Debt) | Required |
| Financial component (budget tracking) | Required |
| Unit testing (minimum 70% backend coverage) | Required |
| CSS framework (Tailwind) | Required |
| JavaScript framework (React) | Required |
| Cloud deployment (accessible via URL) | Required |
| Web API layer | Required |
| File error logging | Required (stretch goal) |
| OWASP ZAP scan – zero Critical issues | Required |
| Accessibility audit – zero errors | Required |
| Session persistence across browser restarts | Required |
| Self-hosted authentication with password reset | Required |
| Deploy to cloud/Windows server | Required (stretch goal) |

Final Acceptance:
The project will be considered accepted when:

- All required criteria above are verified by mentor

- Final presentation is delivered successfully (working application walkthrough)

- Source code is pushed to GitHub repository

- Deployed application URL is provided to mentor

- All documentation is complete