## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Ashli | Fardowsa | Imanol | Travon | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 2
|  | Design architecture | Project Manager | Imanol, Ashli, Travon, Fardowsa | 12 |  | 2 |  | 2 | 0 | 2 |  | 4
| Requirements |  |  |  |  | 9 |  | 9 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Imanol, Ashli, Travon, Fardowsa | 2 |  | 3 |  | 3 | 1 | 3 |  | 7
|  | Analyze | Requirements Engineer | Imanol, Ashli, Travon, Fardowsa | 4 |  | 3 |  | 3 | 1 | 3 |  | 7
|  | Specify | Requirements Engineer | Imanol, Ashli, Travon, Fardowsa | 3 |  | 3 |  | 3 | 2 | 3 |  | 8
| Documentation |  |  |  |  | 28 |  | 38.5 |  |  |  |  | 0
|  | Project Charter | Project Manager | Fardowsa | 2 |  | 3 |  | 0 | 3 | 0 |  | 3
|  | Release Plan | Project Manager | Fardowsa | 2 |  | 3.5 |  | 0 | 3 | 0 |  | 3
|  | Requirements Document | Project Manager | Fardowsa | 5 |  | 6.5 |  | 0 | 6 | 0 |  | 6
|  | Project Plan | Project Manager, Developers | Imanol, Ashli, Travon, Fardowsa | 5 |  | 8 |  | 2 | 6 | 2 | 2 | 12
|  | Architecture Document | Architect | Ashli, Fardowsa | 4 |  | 4 |  | 4 | 2 | 0 |  | 6
|  | Test Report | Tester | Imanol, Ashli, Travon, Fardowsa | 8 |  | 7 |  | 3 | 6 | 3 | 1 | 13
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Fardowsa | 2 |  | 6.5 |  | 0 | 5 | 0 |  | 5
Coding | [12 empty] | 0
Iteration 1: | Development |  |  |  |  | 63 |  | 80 |  |  |  |  | 0
|  | Determine technology needs | Developer(s) | Imanol, Ashli, Travon | 3 |  | 2 |  | 2 |  | 1 | 1 | 4
|  | Research and learn new language and environment | Developer | Imanol, Ashli, Travon | 20 |  | 32 |  | 8 |  | 22 | 9 | 39
|  | Set up proxy server software | Developer | Imanol, | 8 |  | 5 |  | 0 |  | 3 |  | 3
|  | Write basic proxy code | Developer | Imanol | 5 |  | 10 |  | 0 |  | 3.5 |  | 3.5
|  | Implement classes | Developer | Travon | 10 |  | 12 |  | 0 |  | 0 | 12 | 12
|  | Create HTTP handling code | Developer | Ashli | 8 |  | 5 |  | 5 |  | 0 |  | 5
|  | Write code to store user name locally | Developer | Travon, Ashli | 2 |  | 8 |  | 4 |  | 0 | 2 | 6
|  | Write code for managing HTTP session | Developer | Ashli | 5 |  | 4 |  | 4 |  | 0 | 4 | 8
|  | Unit Testing | Developer | Imanol, Ashli, Travon, Fardowsa | 2 |  | 2 |  | 1 | 4 | 1 |  | 6
| Analysis |  |  |  |  | 6 |  | 12 |  |  |  |  | 0
|  | System Testing | Tester | Travon, Imanol | 2 |  | 4 |  | 0 | 1 | 1 | 2 | 4
|  | Bug fix as required | Tester, Developer | Imanol, Ashli, Travon, Fardowsa | 2 |  | 6 |  | 2 | 4 | 2 | 3 | 11
|  | Evaluate needs for next iteration | Project Manager | Fardowsa | 2 |  | 2 |  | 0 | 1 | 0 |  | 1
Iteration 2: | Design |  |  |  |  | 12 |  | 7.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Fardowsa | 2 |  | 0.5 |  | 0 | 2.5 | 0 |  | 2.5
|  | Risk analysis | Project Manager | Fardowsa | 2 |  | 1 |  | 0 | 0.5 | 0 |  | 0.5
|  | Design XML format | Developer | Ashli | 1 |  | 1 |  | 1 |  | 0 |  | 1
|  | Design Perl XML-handling code | Developer | Ashli | 5 |  | 3 |  | 3 |  | 0 |  | 3
|  | Create UI design for balance screen | Developer | Imanol | 2 |  | 2 |  | 0 |  | 2 |  | 2
| Development |  |  |  |  | 22 |  | 30 |  |  |  |  | 0
|  | Review requirements | Developer | Imanol, Ashli, Travon, Fardowsa | 1 |  | 1.5 |  | 0.5 | 2.5 | 0.5 | 1 | 4.5
|  | Create XML parsing code | Developer | Ashli | 5 |  | 3.5 |  | 3.5 |  | 3.5 |  | 7
|  | Handle XML data structure for retrieving balance | Developer | Travon,Ashli | 10 |  | 15 |  | 8 |  | 0 | 1 | 9
|  | Implement UI | Developer | Imanol | 4 |  | 8 |  | 0 |  | 9 |  | 9
|  | Unit Testing | Developer | Imanol, Ashli, Travon, Fardowsa | 2 |  | 2 |  | 2 | 4 | 2 | 3 | 11
| Analysis |  |  |  |  | 6 |  | 5.5 |  |  |  |  | 0
|  | System Testing | Tester | Imanol, Ashli, Travon, Fardowsa | 2 |  | 1.5 |  | 0.5 | 1 | 0.5 | 2 | 4
|  | Bug fix as required | Tester, Developer | Imanol, Ashli, Travon, Fardowsa | 2 |  | 3.5 |  | 2 | 2 | 2 | 2 | 8
|  | Evaluate needs for next iteration | Project Manager | Fardowsa | 2 |  | 0.5 |  | 0 | 2 | 0 |  | 2
Iteration 3: | Design |  |  |  |  | 12 |  | 3.5 |  |  |  |  | 0
|  | Implement any design changes | Project Manager | Imanol, Ashli, Travon, Fardowsa | 2 |  | 0.5 |  | 0.5 | 0.5 | 0.5 |  | 1.5
|  | Risk analysis | Project Manager | Imanol, Ashli, Travon, Fardowsa | 2 |  | 1 |  | 1 | 0.5 | 0.5 |  | 2
|  | Design data structure for RSS location list | Developer | Ashli,Travon | 8 |  | 2 |  | 2 |  | 0 | 4 | 6
| Development |  |  |  |  | 12 |  | 9.5 |  |  |  |  | 0
|  | Review requirements | Developer | Imanol, Ashli, Travon, Fardowsa | 1 |  | 1 |  | 1 | 1 | 1 |  | 3
|  | Create UI for Debts and Budgets Pages | Developer | Imanol | 5 |  | 3.5 |  | 0 | 3.5 | 4 |  | 7.5
|  | Design data structure for debt calculations and budget tracking | Developer | Travon, Ashli | 2 |  | 2 |  | 2 |  | 0 | 2 | 4
|  | Unit Testing | Developer | Imanol, Ashli, Travon, Fardowsa | 4 |  | 3 |  | 2 | 3 | 2 |  | 7
| Analysis |  |  |  |  | 7 |  | 5.5 |  |  |  |  | 0
|  | Acceptance Testing | Tester, Project Manager | Imanol, Ashli, Travon, Fardowsa | 3 |  | 1.5 |  | 1 | 0.5 | 1 | 2 | 4.5
|  | Bug fix as required | Tester, Developer | Imanol, Ashli, Travon, Fardowsa | 4 |  | 4 |  | 1 | 4 | 1 | 5 | 11
Total |  |  |  |  | 189 | 189 | 203 | 203 | 77 | 72.5 | 79 | 58 | 286.5